## REVIEW-SHEET
date | ID | SRS ID | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
2025-04-13 | LH-REVIEW-SRS-001 | SRS-LOGIN-001 | Hala Eldaly | v1.1 | the requirement is vague regarding the type of identifier allowed in the login form. Please clarify whether the system accepts only email address or both email and username for login. Additionally, specify any validation rules for the email field (e.g., format, required field). This helps ensureproper implementation and avoids ambiguity during development and testing. | Ensure that you update the login form to handle both email and username options if applicable, and implement proper email validation (e.g., format, required field) to prevent issues during login and testing. | Ahmed Abozaid | not applicable | closed
2025-04-13 | LH-REVIEW-SRS-002 | SRS-LOGIN-002 | Hala Eldaly | v1.1 | Consider clarifying whether user feedback on failed logins (e.g., email vs. password issue) is intentionally generic for security reason | Please confirm whether the user feedback for failed logins should remain generic (e.g., 'Invalid credentials') for security reasons, or if more specific messages (e.g., 'Incorrect email' or 'Incorrect password') are acceptable. | Ahmed Abozaid | closed | closed
2025-04-14 | LH-REVIEW-SRS-003 | SRS-ID-001 | Hala Eldaly | v1.1 | The SRS requirement does not explicitly mention that the User ID must be unique, as stated in the CRS. | It's recommended to revise the statement to: "A unique User ID shall be generated automatically upon registration" to ensure alignment with the CRS. | Ahmed Abozaid | closed | closed
2025-04-14 | LH-REVIEW-SRS-004 | SRS-PUB-001 | Gehad Ashry | v 1.1 | The SRS does not mention what happens after clicking each button. | Try to clarify that each button will direct the user to a related interface. Recommendation: add "each leading to the respective submission interface" | Ahmed Abozaid | closed | closed
2025-04-14 | LH-REVIEW-SRS-005 | SRS-PUB-002 | Gehad Ashry | v 1.1 | Try to make the requirement a bit clearer so it’s easier to understand for everyone, especially those who are not deeply technical. | Recommendation: The system shall validate video file size before upload and reject files exceeding 100MB, with the message: "Max size: 100MB." | Ahmed Abozaid | closed | closed
2025-04-14 | LH-REVIEW-SRS-006 | SRS-PUB-003 | Gehad Ashry | v 1.1 | The same as the above | Recommendation:The system shall validate audio file size before upload and reject files exceeding 20MB, with the message: "Max size: 20MB." | Ahmed Abozaid | closed | closed
2025-04-14 | LH-REVIEW-SRS-007 | SRS-PUB-004 | Gehad Ashry | v 1.1 | What does the word 'dynamically' refer to? Runtime or on submission? Needs to be clearer | Recommendation: The system shall count words in articles in real-time and prevent submission if the article exceeds 1000 words. | Ahmed Abozaid | closed | closed
2025-04-14 | LH-REVIEW-SRS-008 | SRS-PUB-005 | Gehad Ashry | v 1.1 | Consider replacing “.MP4” with “MP4 format” to improve readability and make it clearer. | Recommendation: The system shall allow only .mp4 video files to be uploaded. If an unsupported format (e.g., .avi) is selected, display: "Only MP4 format is allowed." | Ahmed Abozaid | closed | closed
2025-04-14 | LH-REVIEW-SRS-009 | SRS-PUB-006 | Gehad Ashry | v 1.1 | The same as the above ".MP3" with "MP3 format". | Recommendation: The system shall allow only .mp3 audio files to be uploaded. If another format (e.g., .wav) is selected, display the message: "Only MP3 format is allowed." | Ahmed Abozaid | closed | closed
2025-04-17 | LH-REVIEW-SRS-010 | SRS-REG-004 | Mahmoud Abdelmageed | v 1.1 | The message is very big to be shown inside the password field box(inline) | Recommendation: The message should be shown in a bigger area like next to the password field or in a popup | Ahmed Abozaid | closed | open
2025-04-17 | LH-REVIEW-SRS-011 | SRS-REG-005 | Mahmoud Abdelmageed | v 1.1 | the description has some language mistakes that should be corrected for better understanding of the requirement | Recommendation: The description should be :The system shall ensure that the username is unique. If a duplicate username is detected, an error message shall be displayed, saying : This username is already used | Ahmed Abozaid | closed | closed
2025-04-17 | LH-REVIEW-SRS-012 | SRS-REG-006 | Mahmoud Abdelmageed | v 1.1 | the description has some language mistakes that should be corrected for better understanding of the requirement | Recommendation: The description should be :The system shall validate email to be unique and if not an error message should appear saying : This E-mail is already used | Ahmed Abozaid | closed | closed
2025-04-17 | LH-REVIEW-SRS-013 | SRS-SYS-001 | Mahmoud Abdelmageed | v 1.1 | The CRS did not state that the PC and Web application should have identical feature sets | Recommendation: Rephrase the description to avoid implying that the PC and web applications must have identical feature sets, as differences between platforms make this challenging to implement | Ahmed Abozaid | closed | closed
2025-04-18 | LH-REVIEW-SRS-014 | SRS-ADM-001 | Omar Sherif | v 1.1 | Spelling Error | The word "admains". It should be corrected to "admins" in both constraints. | Ahmed Abozaid | closed | closed
2025-04-18 | LH-REVIEW-SRS-015 | SRS-ADM-001 | Omar Sherif | v 1.1 | Header Consistency | The header "ADMIN Constrain" should be updated to "ADMIN Constraints" for grammatical correctness. | Ahmed Abozaid | closed | closed
2025-04-18 | LH-REVIEW-SRS-016 | SRS-ADM-002 | Omar Sherif | v 1.1 | Inconsistent Naming Convention | In the first column, the ID uses "CONSTRAINS" instead of "CONSTRAINTS". It should be fixed to maintain naming consistency | Ahmed Abozaid | closed | closed

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Hala Eldaly | intial version | 2025-04-13
v1.1 | Hala Eldaly | Added review comments under ID_CONSTRAINTS_REVIEWS, updated the version, and renamed the file to align with the naming convention defined in the project plan. | 2025-04-14
v1.2 | Gehad Ashry | Reviewed Publish and upload feature | 2025-04-14
v1.3 | Mahmoud Abdelmageed | Reviewed Registration and System Constrains | 2025-04-17
v1.4 | Omar Sherif | Reviewed Admin Constraints | 2025-04-18
v1.5 | Hala Eldaly | Close reviewer verification for Login and ID_Constraints | 2025-04-18
v1.6 | Gehad Ashry | Close reviewer verification for Publish and upload feature | 2025-04-18
v1.7 | Mahmoud Abdelmageed | Changed reviewer verification for Registration and System Constrains | 2025-04-19
v1.8 | Omar Sherif | Changed reviewer verification for Admin Constrains | 2025-04-19