## PMP
ID | Reviewer | Version | Review Comments | Actions | Owner | Status | Reviewer verification
LH_REVIEW_PMP_001 | Eman Abusalim | V1.0 | the version history section is currently empty. This section is essential for tracking changes to the Project Management Plan over time. | Please fill in at least the intial version and the authr and the date of creation . | Gehad Ashry | open
LH_REVIEW_PMP_002 | Eman Abusalim | v1.0 | The 'Version History' section appears before the listed 'Table of Contents', although it is listed as one of the content items | Please consider rearranging these sections so that the 'Table of Contents' comes first. This will help readers quickly understand the structure of the document upon opening it. | Gehad Ashry | open
LH_REVIEW_PMP_003 | Eman Abusalim | v1.0 | The objective section provides a clear overall picture of the project, which is great. However, it currently lacks the SMART criteria. | To strengthen it, consider breaking it down into specific, measurable goals with defined deadlines that reflect the key features of the platform. | Gehad Ashry | open
LH_REVIEW_PMP_004 | Eman Abusalim | v1.0 | The current Reporting Process Flow presents a basic outline of the reporting stages. However, the steps need more detail regarding responsibilities, timing, communication channels, and tools used to ensure a smooth and consistent reporting cycle. | Please consider expanding each step of thr reporting process flow for better clarity and execution. | Gehad Ashry | open
LH_REVIEW_PMP_005 | Eman Abusalim | v1.0 | In the configuration management plan section The Hyberlink in the configuration items is not clickable | please make the link redirect to the Configuration Item List so that the reader can easly get the 2- Configuration Items (CI) | Gehad Ashry | open
LH_REVIEW_PMP_006 | Eman Abusalim | v1.0 | The work out of scope is writdoten very well howeverwe need to be more spacific about activites we will do | Add the following : -unit testing -Desktop application -Application programming interface | Gehad Ashry | open
LH_REVIEW_PMP_007 | Eman Abusalim | v1.0 | in the Project Scope section, the line "Users can follow categories and engage with the content"is too broad and may cause confusion regarding the actual features of the system. | It is recommended to revise this statement to: "Users can follow categories and receive updates for new content." This alternative better aligns with the defined features in the scope and avoids implying unsupported interactions such as commenting, liking, or sharing. | Gehad Ashry | open
LH_REVIEW_PMP_008 | Eman Abusalim | v1.0 | he scope item "Admin Features: Admins will have control over content management and user moderation" may need clarification. The current plan assumes that the admin's only action is to delete content, but this was not specified by the customer. | It is recommended to confirm the expected admin capabilities with the customer before finalizing the scop | Gehad Ashry | open
LH_REVIEW_PMP_009 | Eman Abusalim | v1.0 | he matrix uses the abbreviation 'RICARS,' which appears to be a typographical error. The correct acronym is 'RASIC.' | The matrix should be updated to reflect the proper roles of Responsible, Accountable, Support, Informed, and Consulted. Please revise the matrix for accuracy and clarity." | Gehad Ashry | open
LH_REVIEW_PMP_010 | Eman Abusalim | v1.0 | There seems to be a conflict between the "Out of Work Scope" section and the "Work Breakdown Structure" (WBS). The "Out of Work Scope" lists "Integration with external content providers or third-party databases" as excluded, which suggests that the project will not involve external integrations. However, in the WBS, the tasks "Define system and database architecture" and "Develop business logic and database integration" are included, which might imply integration with external databases or services. | Please clarify in the WBS that the "database integration" refers to internal system/database integration and not external content providers, as this will align with the stated project scope. If any external integrations are planned, they should be explicitly mentioned as part of the scope or excluded from the WBS accordingly. | Gehad Ashry | open
LH_REVIEW_PMP_011 | Eman Abusalim | v1.0 | After reviewing the Communication Matrix, I suggest modifying the frequency for the Risk Updates and Progress Reporting sections. | Both of these communication goals could be set to "As Needed" rather than weekly, to ensure that updates are only provided when there is significant progress or risk-related developments that require stakeholder attention. This would help in keeping the communication focused and relevant. | Gehad Ashry | open
LH_REVIEW_PMP_012 | Eman Abusalim | v1.0 | It should be noted that the team standup meetings occur on Saturday, Monday, and Wednesday, rather than daily. This adjustment will provide a clearer understanding of the actual meeting schedule and help ensure proper communication flow among team members. |  | Gehad Ashry

## SIQ
ID | Reviewer | Version | Review Comments | Actions | Owner | Status | Reviewer verification
LH_REVIEW_SIQ_001 | Hala Eldaly | 6f18b88 | IDs naming convention doesn't follow the rules. Registration feature is written incorrectly. SIQ_02 – This question should be: (Should the password contain a combination of letters, numbers, and special characters?) NOT: (Should the password be a combination between numbers, chars and special chars?) SIQ_06 – It's not related to the registration feature, but to performance. SIQ_08 – This question should be: (Should the website include exactly 5 content categories?) NOT: (Should there be 5 categories?) SIQ_10 – This question should be: (Should the maximum allowed audio recording size be 20 MB?) NOT: (Should the maximum size for recordings not exceed 20mb?) SIQ_11 – Confusing: chars vs. words >> Should the maximum length of an article be limited to 1000 words? SIQ_13 – "Mp3" → Should the audio format be MP3 only? SIQ_14 – This question should be: (Should a notification system be available through the website?) NOT: (A notification system should be available via website?) SIQ_16 – Incorrect structure >> Should the admin features include removing articles, videos, and audio files? | Should modify naming convention. Be clear about the difference between chars (characters) and words. Focus on consistent capitalization ( use MP3 instead of Mp3). Use direct, question-style sentences to make the meaning easily understandable. Keep sentence structure simple and to the point to avoid confusion. | Mahmoud Radi | closed | open

## CRS
ID | Reviewer | Version | Review Comments | Actions | Owner | Status | Reviewer verification
LH_REVIEW_CRS_001 | Ahmed Abuzaid | 0ca4136 | 1_the sheet name is named sheet 1 2_the feature column not useful in this case | 1_name the sheet according naming convetion "LH_CRS" 2_we can suffice with the feature name in the id | Omar Sherif | closed | open
LH_REVIEW_CRS_002 | Ahmed Abuzaid | 0ca4136 | for the CRS item LH_CRS_005 – System Constrain, the current phrasing “web-based system/PC based” is a bit unclear | can you make it more clear | Omar Sherif | closed | open
LH_REVIEW_CRS_003 | Ahmed Abuzaid | 0ca4136 | no comment on " LH_CRS_ID-CONSTRAINS_006" | no action | Omar Sherif | closed | closed
LH_REVIEW_CRS_004 | Ahmed Abuzaid | 0ca4136 | no comment on "LH_CRS_ADMIN-CONSTRAINS_007" | no action | Omar Sherif | closed | closed
LH_REVIEW_CRS_005 | Omar Sherif | 0ca4136 | The ID was written using underscores (_) instead of hyphens (-). According to the PMP standard, hyphens should be used for ID formatting. | Update all IDs to replace underscores (_) with hyphens (-) to ensure compliance with the PMP format guidelines. | Ahmed Abuzaid | open | open