## VERSION_HISTORY
version_number | Author | Updates | Date
V1.0 | Eman(PO) | planing for: 1:Test Cases (TC) 2:Wire Frame(WF) 3:Software Requirment Specifications 4:updating the pmp based on comments | 2025-04-14

## RELEASE_PLAN
WORK_PACKAGE _ID | Task_ID | type (Create/Review) | Estimated Hours | Actual Hours | Assigned Member
WP_RP | LH_RP_SHEET_Create_1 | Create | 2hr | 4hr | Eman
| LH_RP_BACKLOG_Create_2 | Create | 2hr |  | Eman
| LH_RP_TRACKING TASKS | Create | 1:30hr |  | Eman
WP_SRS | LH_SRS_REGISTERATION_1 | Create | 1:30hr |  | Ahmed
| LH_SRS_REGISTERATION_2 | Review | 45min |  | Mahmoud
| LH_SRS_LOGIN_3 | Create | 1hr |  | Ahmed
| LH_SRS_LOGIN_4 | Review | 1hr |  | Hala
| LH_SRS_NAVIGATION_5 | Create | 30min |  | Ahmed
| LH_SRS_NAVIGATION_6 | Review | 45min |  | Omar
| LH_SRS_PUBLISH&UPLOAD_7 | Create | 1hr |  | Ahmed
| LH_SRS_PUBLISH&UPLOAD_8 | Review | 30min |  | Gehad
| LH_SRS_NOTIFICATION_9 | Create | 20min |  | Ahmed
| LH_SRS_NOTIFICATION_10 | Review | 1hr |  | Eman
| LH_SRS_SYSTEM CONSTRAINS_11 | Create | 20min |  | Ahmed
| LH_SRS_SYSTEM CONSTRAINS_12 | Review | 45min |  | Mahmoud
| LH_SRS_ADMIN CONSTRAINS_13 | Create | 20min |  | Ahmed
| LH_SRS_ADMIN CONSTRAINS_14 | Review | 45min |  | Omar
| LH_SRS_ID CONSTRAINS_15 | Create | 20min |  | Ahmed
| LH_SRS_ID CONSTRAINS_16 | Review | 1hr |  | Hala
WP_TC | LH_TC_REGISTERATION_1 | Create | 2hr |  | Omar
| LH_TC_REGISTERATION_2 | Review | 1hr |  | Eman
| LH_TC_LOGIN_3 | Create | 1:30 hr |  | Hala
| LH_TC_LOGIN_4 | Review | 1hr |  | Mahmoud
| LH_TC_NAVIGATION_5 | Create | 1hr |  | Gehad
| LH_TC_NAVIGATION_6 | Review | 1hr |  | Ahmed
| LH_TC_PUBLISH&UPLOAD_7 | Create | 1:30hr |  | Ahmed
| LH_TC_PUBLISH&UPLOAD_8 | Review | 45min |  | omar
| LH_TC_NOTIFICATION_9 | Create | 1:30hr |  | Mahmoud
| LH_TC_NOTIFICATION_10 | Review | 45min |  | Gehad
| LH_TC_SYSTEM CONSTRAINS_11 | Create | 1hr |  | Gehad
| LH_TC_SYSTEM CONSTRAINS_12 | Review | 1hr |  | Hala
| LH_TC_ADMIN CONSTRAINS_13 | Create | 1:30hr |  | Eman
| LH_TC_ADMIN CONSTRAINS_14 | Review | 45min |  | omar
| LH_TC_ID CONSTRAINS_15 | Create | 1:30hr |  | Mahmoud
| LH_TC_ID CONSTRAINS_16 | Review | 1:30hr |  | Ahmed
WP_WF | LH_WF_REGISTERATION_1 | Create | 2hr |  | Gehad
| LH_WF_REGISTERATION_2 | Review | 30min |  | Ahmed
| LH_WF_LOGIN_3 | Create | 40min |  | Mahmoud
| LH_WF_LOGIN_4 | Review | 45min |  | Omar
| LH_WF_NAVIGATION_5 | Create | 3hr |  | Omar
| LH_WF_NAVIGATION_6 | Review | 1hr |  | Hala
| LH_WF_PUBLISH&UPLOAD_7 | Create | 2hr |  | Hala
| LH_WF_PUBLISH&UPLOAD_8 | Review | 1:30 |  | Gehad
| LH_WF_NOTIFICATION_9 | Create | 40 |  | Ahmed
| LH_WF_NOTIFICATION_10 | Review | 30min |  | Mahmoud
WP_PMP_UPDATE | LH_PMP_UPDATE_SEC1&2&3&4&5 | Create | 2hr |  | Hala | 1H
| LH_PMP_UPDATE_SEC_6&10 | Create | 3hr |  | Eman | 1H
| LH_PMP_UPDATE_SEC_7&8 | Create | 3hr |  | Gehad | 1H
| LH_PMP_UPDATE_SEC_9&13 | Create | 2hr |  | Ahmed | 1H
| LH_PMP_UPDATE_SEC_11&12 | Create | 3hr |  | Mahmoud | 1H
| LH_PMP_UPDATE_SEC_14&15 | Create | 3hr |  | Omar | 2H
| LH_PMP_UPDATE_SEC1&2&3&4&5 | Review | 2hr |  | Gehad
| LH_PMP_UPDATE_SEC_6&10 | Review | 2hr |  | Ahmed
| LH_PMP_UPDATE_SEC_7&8 | Review | 2hr |  | omar
| LH_PMP_UPDATE_SEC_9&13 | Review | 2hr |  | Hala
| LH_PMP_UPDATE_SEC_11&12 | Review | 2hr |  | Mahmoud
| LH_PMP_UPDATE_SEC_14&15 | Review | 2hr |  | Eman

## ESTIMATED_TIME
Name | Available Time | Planed Time | Actual Time
Eman | 18 | 14
Omar | 14 | 13:45
Hala | 15:00 | 11:30
Gehad | 20 | 11:45
Mahmoud | 13 | 11:40
Ahmed | 17:00 | 14:30
Total | 97hr | 77hr