## Version History
Version Number | Author | Updated Section | Date
v1.0 | Mahmoud abdelmageed | intial version | 2025-04-16
v1.1 | Mahmoud abdelmageed | Added crucial missing review points regarding the TC_ID column and modified Filename review and Status and Actual result column | 2025-04-18
v1.2 | Mahmoud abdelmageed | Added reviews for the new version of the Testcases file | 2025-04-19
v1.3 | Hala Eldaly | Set Owner Status to closed | 2025-04-21
v1.4 | Mahmoud abdelmageed | Set Reviewer verification to closed | 2025-04-23

## Review sheet
date | Review ID | Reviewed Entity | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
2025-04-16 | LH_REVIEW_TC_LOGIN_001 | LH-TC-Login-001 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability 3- invalid test data, user can only login using email and password | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_002 | LH-TC-Login-002 | Mahmoud abdelmageed | 1.0 | 1-user is already registered precondition is unnecessary 2- there is no space between the username and the password in the test data column 3-in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-remove the user is already registered precondition 2-change test data to the correct form 3-separate username(email) and password to different lines or add space between username and password 4-put each step in the steps column in a new line | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_003 | LH-TC-Login-003 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_004 | LH-TC-Login-004 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_005 | LH-TC-Login-005 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_006 | LH-TC-Login-006 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_007 | LH-TC-Login-007 | Mahmoud abdelmageed | 1.0 | 1-this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_008 | LH-TC-Login-008 | Mahmoud abdelmageed | 1.0 | 1-this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_009 | LH-TC-Login-009 | Mahmoud abdelmageed | 1.0 | 1-this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_010 | LH-TC-Login-010 | Mahmoud abdelmageed | 1.0 | 1-this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_011 | File name | Mahmoud abdelmageed | 1.0 | 1-File name is using - for spacing instead of _ 2-the word sheet is not necessary | 1-Change filename to follow the naming convention 2-Remove the word SHEET from the name | Hala Eldaly | Closed | Closed
2025-04-16 | LH_REVIEW_TC_LOGIN_012 | Sign up button | Mahmoud abdelmageed | 1.0 | 1-the feature (new user? Sign up) button was not tested | 1-include testcases to test this feature | Hala Eldaly | Closed | Closed
2025-04-18 | LH_REVIEW_TC_LOGIN_013 | TC_ID column | Mahmoud abdelmageed | 1.0 | 1-This column is redundant because there is already an id column 2-the SRS_ID column is missing , which will be used for traceability | 1-Replace the TC_ID column with SRS_ID for traceability means which includes the SRS ID that the TC is related to | Hala Eldaly | Closed | Closed
2025-04-18 | LH_REVIEW_TC_LOGIN_014 | Status column and Acutal results column | Mahmoud abdelmageed | 1.0 | 1-There is no status and Acutual results column which are necessary for tc execution | 1-Add Status column with 4 choices Pass,Fail,Blocked,Not executed and the default placeholder is Not executed | Hala Eldaly | Closed | Closed
2025-04-19 | LH_REVIEW_TC_LOGIN_015 | LH-TC-Login-001 | Mahmoud abdelmageed | 1.1 | 1-Test Data for login is Username and password and the user can only login using E-mail and password | 1-Change the Username to E-mail | Hala Eldaly | Closed | Closed
2025-04-19 | LH_REVIEW_TC_LOGIN_016 | LH-TC-Login-002 | Mahmoud abdelmageed | 1.1 | 1-Test Data for login is Username and password and the user can only login using E-mail and password 2-The username(email) provided is an invalid E-mail for the front-end validation only and there is no testcase covering the invalid E-mail( an email that is not registered) | 1-Change the Username to E-mail 2-Create a testcase with an invalid E-mail in the correct email form to bypass front-end validation eg:(invalidemail@gmail.com) | Hala Eldaly | Closed | Closed
2025-04-19 | LH_REVIEW_TC_LOGIN_017 | LH-TC-Login-003 | Mahmoud abdelmageed | 1.1 | 1-Test Data for login is Username and password and the user can only login using E-mail and password 2- Testcase testing wrong password should include a Valid E-mail and this tc has invalid E-mail | 1-Change the Username to E-mail 2-Use Valid email for this Testcase since the user is already registered is a precondition | Hala Eldaly | Closed | Closed
2025-04-19 | LH_REVIEW_TC_LOGIN_018 | LH-TC-Login-004 | Mahmoud abdelmageed | 1.1 | 1-Test Data for login is Username and password and the user can only login using E-mail and password | 1-Change the Username to E-mail | Hala Eldaly | Closed | Closed
2025-04-19 | LH_REVIEW_TC_LOGIN_019 | LH-TC-Login-006 | Mahmoud abdelmageed | 1.1 | 1-Test Data for login is Username and password and the user can only login using E-mail and password | 1-Change the Username to E-mail | Hala Eldaly | Closed | Closed