## REVIEW-SHEET
date | ID | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
2025-04-04 | LH_REVIEW_SIQ_001 | Hala Eldaly | b4842b1 | IDs naming convention doesn't follow the rules. | Review and update all ID naming conventions to align with the defined project standards | Mahmoud Radi | closed | closed
|  |  |  | Registration feature is written incorrectly. | Please review spelling |  | closed | closed
|  |  |  | SIQ_02 – This question should be: (Should the password contain a combination of letters, numbers, and special characters?) NOT: (Should the password be a combination between numbers, chars and special chars?) | Be clear about the difference between chars (characters) and words. |  | closed | closed
|  |  |  | SIQ_06 – It's not related to the registration feature, but to performance. | Reclassify SIQ_06 under performance category instead of registration. |  | closed | closed
|  |  |  | SIQ_08 – This question should be: (Should the website include exactly 5 content categories?) NOT: (Should there be 5 categories?) | Update SIQ_08 wording to: "Should the website include exactly 5 content categories?" for clarity. Update SIQ_08 wording to: "Should the website include exactly 5 content categories?" for clarity. |  | closed | closed
|  |  |  | SIQ_10 – This question should be: (Should the maximum allowed audio recording size be 20 MB?) NOT: (Should the maximum size for recordings not exceed 20mb?) | Aim for clear and formal phrasing in question wording to avoid ambiguity. |  | closed | closed
|  |  |  | SIQ_11 – Confusing: chars vs. words >> Should the maximum length of an article be limited to 1000 words? | Clarify SIQ_11 by specifying "1000 words" instead of using ambiguous terms like "chars" |  | closed | closed
|  |  |  | SIQ_13 – "Mp3" → Should the audio format be MP3 only? | Focus on consistent capitalization ( use MP3 instead of Mp3) |  | closed | closed
|  |  |  | SIQ_14 – This question should be: (Should a notification system be available through the website?) NOT: (A notification system should be available via website?) | Rephrase SIQ_14 to: "Should a notification system be available through the website?" to maintain consistency and proper question format. |  | closed | closed
|  |  |  | SIQ_16 – Incorrect structure >> Should the admin features include removing articles, videos, and audio files? | Revise SIQ_16 to: "Should the admin features include removing articles, videos, and audio files?" to correct the sentence structure. |  | closed | closed

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Hala Eldaly | intial version | 2025-04-07
v1.1 | Hala Eldaly | I separated the Review Comments into individual rows for better control and organization. | 2025-04-12