## REVIEW-SHEET
date | ID | Reviewed Entity | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
17/4/2025 | LH-CRS-Review-001 | LH-CRS-NOTIFICATION-001 | Eman | V1.0 | At the notification feature the first crs need to be more atomic to contain only one action the user could do | make the CRS is as follow""Users can follow and unfollow specific categories." | Omar | closed | closed
17/4/2025 | LH-CRS-Review-002 | LH-CRS-NOTIFICATION-002 | Eman | V1.1 | At notification feature the CRS is too vauge and does not explain what the customer want the system do | write the CRS as this"The system must notify users within the website interface when new content is added to a followed category." | Omar | closed | closed
30/4/2025 | LH-CRS-Review-003 | LH-CRS-USERHOME-002 | Ahmed Abuzaid | v2.0 | in this CRS you mention a lot of detalies that will not important for the customer and it can be a SRS | it can only be "The home page must dynamically fetch and display notifications for new articles in categories the user follows" | hala | closed | open
30/4/2025 | LH-CRS-Review-004 | LH-CRS-USERHOME-003 | Ahmed Abuzaid | v2.0 | in this CRS you mention a lot of detalies that will not inmportant for the customer and it can be a SRS | it can only be "Posts from followed categories must be listed on the user home page" | hala | closed | open
30/4/2025 | LH-CRS-Review-005 | LH-CRS-DELETEPOST-001 | Gehad Ashry | v2.1 | Watch out for grammatical errors and typos that may reduce clarity. | Replace with: "The admin has the ability to delete any post (articles, videos, or audio recordings) through the 'Delete Post' page." | Ahmed Abuzaid | closed | open
30/4/2025 | LH-CRS-Review-006 | LH-CRS-DELETEPOST-002 | Gehad Ashry | v2.1 | This sentence is grammatically incorrect and slightly confusing in its current form. The phrase "searching about posts" should be revised for clarity, and "its username" should be "their username" since it refers to a user. | Replace with: "The admin can delete a post by searching for a user's posts using their username." | Ahmed Abuzaid | closed | open
30/4/2025 | LH-CRS-Review-007 | LH-CRS-DELETEPOST-003 | Gehad Ashry | v2.1 | Try rewording it to better reflect the case where a user exists but has no posts. | Replace with: "If no posts are found for the entered username, an informative message must be displayed." | Ahmed Abuzaid | closed | open
30/4/2025 | LH-CRS-Review-008 | LH-CRS-DELETEPOST-004 | Gehad Ashry | v2.1 | This sentence is also unclear and repeats part of the previous requirement. If the system handles both "no posts" and "user not found" cases differently, clarify each. Otherwise, you might consider combining them. | Combine both of (003 & 004) but if the system handles them differently Replace with: "If the entered username does not exist in the system, an informative message must be displayed." | Ahmed Abuzaid | closed | open
30/4/2025 | LH-CRS-Review-007 | LH-CRS-DELETEPOST-005 | Gehad Ashry | v2.1 | This sentence is mostly clear, but there's a typo in "pf" (should be "of"). Also, consider rewording slightly to improve tone and flow. | Replace with: "The admin can return to the admin home page by clicking the website logo." | Ahmed Abuzaid | closed | open
30/4/2025 | LH-CRS-Review-008 | LH-CRS-PUBLISHAUDIO-001 | Ahmed Abuzaid | v2.2 | this CRS contain a lot of details that might be important in SRS not here and it can more simple and to the point | it can be: "Only registered and logged-in users can access the audio publishing interface that found in a publish drop down in categories page" | Gehad Ashry | open | open
30/4/2025 | LH-CRS-Review-009 | LH-CRS-PUBLISHAUDIO-002 | Ahmed Abuzaid | v2.2 | this CRS contain a lot of details that might be important in SRS not here and it can more simple and to the point | it can be: "Only registered and logged-in users can recored a voice note and set a title for it then publish it " | Gehad Ashry | open | open
30/4/2025 | LH-CRS-Review-010 | LH-CRS-PUBLISHAUDIO-003 | Ahmed Abuzaid | v2.2 | you mentioned that the audio recorde will have two limits "one for duration of record and another for its size" ,but I think we can only suffice with only duration as the 5 minutes audio recorde ussaully doesn't exceeds 20 MB | it can be: "The user can record a voice message for up to 5 minutes. If the time limit is exceeded,a message will appear explaining this." | Gehad Ashry | open | open
30/4/2025 | LH-CRS-Review-011 | LH-CRS-PUBLISHARTICLE-003 | Mahmoud Abdelmageed | v2.2 | The maximum words limit is not shown to the user | clarify that the maximum words should be visible to the user in the counter as shown in the wireframe | Gehad Ashry | open | open
2025-01-05 | LH-CRS-Review-012 | Missed VERSION-HISTORY Modify | Hala Eldaly | v2.4 | you don't update version in VERSION-HISTORY | You should add [v2.4 update the admin constraints by modifying the delete user constraints] | EmanAbusalim | closed | open
2025-01-05 | LH-CRS-Review-013 | No name added to owner column | Hala Eldaly | v2.4 | owner column is empty | add your name | EmanAbusalim | closed | open
2025-01-05 | LH-CRS-Review-014 | LH-CRS-DELETEUSER_001 | Hala Eldaly | v2.4 | The admin has the ability to delete any user from the delete user page [not delete post page] | " delete post" → should be " delete user" | EmanAbusalim | closed | open
2025-01-05 | LH-CRS-Review-015 | LH-CRS-DELETEUSER_003 | Hala Eldaly | v2.4 | Spelling mistakes | "ind" → should be "and" "id" → should be "ID" "apear" → should be "appear" | EmanAbusalim | open | open
2025-02-05 | LH-CRS-Review-016 | LH-CRS-ADMINHOME-003 | Omar Sherif | v2.6 | Dropdown is present, but lacks confirmation/security details in description or wireframe. | Add confirmation and secure-action behavior to the description. | Hala Eldaly | open | Open
2025-02-05 | LH-CRS-Review-017 | LH-CRS-PUBLISHVIDEO-002 | Omar Sherif | v2.6 | Spelling mistakes | Fix: capitalized "he" → "The" and smoothed out the sentence structure | Hala Eldaly | open | Open
2025-02-05 | LH-CRS-Review-018 | LH-CRS-PUBLISHVIDEO-003 | Omar Sherif | v2.6 | Spelling mistakes | (Fix: Changed “formats” to singular “format” since only .mp4 is allowed. | Hala Eldaly | open | Open
2025-02-05 | LH-CRS-Review-016 | LH-CRS-REGISTRATION-008 | Ahmed Abuzaid | v2.6 | this CRS is already mentioned in LH-CRS-REGISTRATION-005 | so we can be satisfied with the LH-CRS-REGISTRATION-005 and the constraints can be mentioned in SRS | omar sherif | open | open
2025-02-05 | LH-CRS-Review-017 | LH-CRS-REGISTRATION-009 | Ahmed Abuzaid | v2.6 | this CRS is already mentioned in LH-CRS-REGISTRATION-006 | so we can be satisfied with the LH-CRS-REGISTRATION-006 and any more details can be mentioned in SRS | omar sherif | open | open
2025-02-05 | LH-CRS-Review-018 | LH-CRS-REGISTRATION-010 | Ahmed Abuzaid | v2.6 | you mention "as seen in the wireframe" | we don't need to mention that as CRS wrote before the wireframe design an we can be satisfied by (All error messages must be displayed in a consistent and visible location, such as beneath the relevant input field or in a designated error message area) | omar sherif | open | open

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Eman | review the notification feature and ask for some updates on it | 2025-04-17
v1.1 | omar sherif | Review the system constraints and closed the reviewed notifications CRS | 2025-04-21
v1.2 | Hala Eldaly | review the login and No Comments | 2025-04-29
v1.3 | Ahmed Abuzaid | review the user home page and ask to modify some of them | 2025-04-30
v1.4 | Gehad Ashry | review Admin Constraints for Deleting Post feature | 2025-04-30
v1.5 | Ahmed Abuzaid | 1/modify delete post CRSs according to reviewer comments 2/review publish audio CRSs, add my comments , ask for some modifications | 2025-04-30
v1.6 | Mahmoud Abdelmageed | Reviewed Publish article CRS | 2025-04-30
v1.7 | Hala Eldaly | Reviewed the 'Delete User' feature in the Admin Constraints section | 2025-05-01
v1.8 | Hala Eldaly | close owner state for USERHOME feature | 2025-05-01
v1.9 | omar sherif | Reviewed publish Video and admin home | 2025-05-02
v1.10 | Eman | update owner status | 2025-05-02
v1.11 | Ahmed Abuzaid | reviewed registration CRS | 2025-05-02