## LH_TC_NOTIFICATION_REVIEWS
Date | Review ID | Reviewed Entity | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
2025-04-21 | LH-TC-NOTIGICATION-REVIEW-001 | LH_TC_NOTIFICATION file | Gehad Ashry | v1.0 | Notification testcases and Tab name do not follow the project's naming convention. | Please ensure the test case ID follows the project's naming convention: it should begin with 'LH' and use hyphens (-) instead of underscores (_) to separate segments (LH-TC-SECTION-ID). Also ensure that the tab is named after the feature you are working with: (LH_TC_FEATURENAME). | Mahmoud Abdelmageed | Closed | Closed
2025-04-21 | LH-TC-NOTIGICATION-REVIEW-002 | LH-TC-NOTIFICATION-001 | Gehad Ashry | v1.0 | 1-Test data is missing — while not critical to the logic, it is important for consistency and reproducibility across environments. 2-The expected results are generally valid, but it’s unclear how the "Follow" button should appear after being toggled — this should be explicitly stated. | 1-Add a specific category ("Sports" or any predefined one) as test data. 2-Clarify the expected button label/state after toggling (changes from "Follow" to "Following" or similar). | Mahmoud Abdelmageed | Closed | Closed
2025-04-21 | LH-TC-NOTIGICATION-REVIEW-003 | LH-TC-NOTIFICATION-002 | Gehad Ashry | v1.0 | 1-Test Data: The current test data entry is vague. Including a specific example of an unread notification ("You have a new message from Admin") would improve reproducibility. 2-Expected Results: The results are valid, but they would benefit from more specificity. For example, describe how the unread notification should appear in the dropdown (e.g., title, message snippet, timestamp if applicable). | 1-Add a sample unread notification to the Test Data section to enhance clarity. 2-Update the Expected Results to describe the expected appearance or structure of the notification items in the dropdown (within the limits of the SRS). | Mahmoud Abdelmageed | Closed | Closed
2025-05-12 | LH-TC-NOTIGICATION-REVIEW-004 | LH-TC-NOTIFICATION-005 LH-TC-NOTIFICATION-003 | Mahmoud Abdelmageed | v2.0 | The notifications are not a dropdown | Adjust testcase so that the notifications are a section not a dropdown | Hala Eldaly | Closed | Closed

## Version History
Version Number | Author | Updated Section | Date
v1.0 | Gehad Ashry | intial version | 2025-04-21
v1.1 | Mahmoud Abdelmageed | Changed the owner status | 2025-04-21
v1.2 | Gehad Ashry | Verified Test cases after update | 2025-04-21
V2.0 | Mahmoud Abdelmageed | Reviewed v2.0 | 2025-05-12
V2.1 | Mahmoud Abdelmageed | closed reviewer status | 2025-05-12