## LH_WF_DELETEPOST_REVIEW
date | ID | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
29/4/2025 | LH-WF-DELETEPOST-REVIEW-001 | Omar Sherif | v1.0 | The wireframe refers to "Post" deletion, but the SRS specifies articles, videos, and audio files. This creates ambiguity. | Update terminology to reflect all content types (e.g., "Delete Content" instead of "Delete Post"). Add visual indicators for content type (e.g., icons or labels like "Article," "Video"). | Eman | open | open
29/4/2025 | LH-WF-DELETEPOST-REVIEW-002 | Omar Sherif | v1.0 | The "Delete" button lacks a confirmation step, increasing risk of accidental deletions. | Add a confirmation modal with: - Message: "Delete [Video] 'Title'? This action cannot be undone." - Buttons: "Cancel" (primary) / "Delete" (secondary, red). | Eman | open | open
29/4/2025 | LH-WF-DELETEPOST-REVIEW-003 | Omar Sherif | v1.0 | The "Delete" button is placed near the search bar, risking accidental clicks. | Reposition the "Delete" button below the content details and style it as a secondary action (e.g., red outline). | Eman | open | open

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Omar Sherif | Initial version of review on Delete Post wireframe | 2025-04-29