## VERSION_HISTORY
version_number | Author | Updates | Date
v4.0 | Ahmed Abuzaid | planing for: 1: coding the featurs 2:update test cases 3:excute test cases | 2025-05-10

## RELEASE_PLAN
Release #5 Planning
Start Date | End Date
2025-10-05 | 17/5/2025
Deliverables
full tested software - comments from last release - PM Tasks
Customer: amr | Coach:youseff
compeletion rate |  |  | individuals
logged | 116.5 |  | team member | estimated | actual | %
time for not started | 1.5 |  |  | 14.5 | 14 | 96.5517
time for inprogress | 6 |  | gehad | 13 | 18.75 | 144.2308
total | 124 |  | hala | 12 | 16.5 | 137.5
% compeletion | 93.9516 |  | Ahmed | 23.5 | 26.5 | 112.766
|  |  | mahmoud | 28.5 | 30 | 105.2632
|  |  | omar | 18 | 24 | 133.3333
|  |  | total | 109.5 | 129.75
WORK_PACKAGE _ID | Task_ID | type (Create/Review) | Estimated Hours | Actual Hours | Assigned Member | Status | % of compeletion | remaining time for inprogress tasks
WP_PO TASKS | LH_RELEASEPLAN_001 | Create | 3 | 4 | Eman | in progress | 80% | 1
| LH_BACKLOG_002 |  | 2 | 1.5 | Ahmed | Complete
| LH_TRACKING TASKS_003 |  | 2 | 3.5 | Ahmed | Complete
| LH_ISSUESANDLOGS_004 |  | 0.5 | 0.5 | Eman | Complete
WP_TC | LH_TC_LOGIN_001 | Create | 1 | 1.5 | Gehad | Complete
| LH_TC_REGISTER_002 |  | 2 | 1.5 | Omar | Complete
| LH_TC_USERHOME_003 |  | 1 | 1 | Hala | Complete
| LH_TC_CATEGORIES_004 |  | 1 | 1.5 | omar | Complete
| LH_TC_PUBLISHARTICLE_005 |  | 1 | 2 | Gehad | Complete
| LH_TC_PUBLISHAUDIO_006 |  | 1 | 1.5 | Ahmed | Complete
| LH_TC_PUBLISHVIDEO_007 |  | 1 | 1 | Hala | Complete
| LH_TC_ADMINHOME_008 |  | 1 | 1 | Hala | Complete
| LH_TC_DELETEPOST_009 |  | 1 | 0.75 | Ahmed | Complete
| LH_TC_DELETEUSER_010 |  | 1 | 1.25 | Ahmed | Complete
| LH_TC_NOTIFICATION_011 |  | 1 | 1 | Hala | Complete
| LH_TC_SYSTEMCONSTRAINS_012 |  | 1 | 0.75 | Ahmed | Complete
| LH_TC_LOGIN_013 | Review | 0.5 | 0.5 | Hala | Complete
| LH_TC_REGISTER_014 |  | 0.5 | 1.5 | Ahmed | Complete
| LH_TC_USERHOME_015 |  | 0.5 | 0.5 | Ahmed | Complete
| LH_TC_CATEGORIES_016 |  | 0.5 | 1 | Hala | Complete
| LH_TC_PUBLISHARTICLE_017 |  | 0.5 | 0.5 | Mahmoud | Complete
| LH_TC_PUBLISHAUDIO_018 |  | 0.5 | 0.5 | Gehad | Complete
| LH_TC_PUBLISHVIDEO_019 |  | 0.5 | 0.75 | Omar | Complete
| LH_TC_ADMINHOME_020 |  | 0.5 | 0.75 | Omar | Complete
| LH_TC_DELETEPOST_021 |  | 0.5 | 0.5 | Gehad | Complete
| LH_TC_DELETEUSER_022 |  | 0.5 | 1 | Hala | Complete
| LH_TC_NOTIFICATION_023 |  | 0.5 | 2 | Mahmoud | Complete
| LH_TC_SYSTEMCONSTRAINS_024 |  | 0.5 | 1 | Mahmoud | Complete
WP_WRITINGCODE | LH_CODE_USERHOME_003 | Create | 4 | 5 | Mahmoud | Complete
| LH_CODE_CATEGORIES_004 |  | 4 | 4 | Mahmoud | Complete
| LH_CODE_PUBLISHARTICLE_005 |  | 3 | 3.5 | Ahmed | Complete |  | 3.5
| LH_CODE_PUBLISHAUDIO_006 |  | 3 | 4.5 | Ahmed | Complete |  | 3.5
| LH_CODE_PUBLISHVIDEO_007 |  | 3 | 3 | Ahmed | Complete |  | 3.5
| LH_CODE_ADMINHOME_008 |  | 4 | 2 | Mahmoud | Complete
| LH_CODE_DELETEPOST_009 |  | 4 | 4.5 | Mahmoud | Complete
| LH_CODE_DELETEUSER_010 |  | 4 | 4 | Mahmoud | Complete
| LH_CODE_LOGIN_011 |  | 3 | 3 | Mahmoud | Complete
| LH_CODE_REGISTER_012 |  | 3 | 3 | Mahmoud | Complete
| LH_CODE_USERHOME_013 | Review | 1 | 2 | Hala | Complete
| LH_CODE_CATEGORIES_014 |  | 1 | 2 | Hala | Complete
| LH_CODE_PUBLISHARTICLE_015 |  | 1 | 1.5 | Omar | Complete
| LH_CODE_PUBLISHAUDIO_016 |  | 1 | 1.5 | Omar | Complete
| LH_CODE_PUBLISHVIDEO_017 |  | 1 | 1.5 | Omar | Complete
| LH_CODE_ADMINHOME_018 |  | 1 | 2 | Gehad | Complete
| LH_CODE_DELETEPOST_019 |  | 1 | 1 | Gehad | Complete
| LH_CODE_DELETEUSER_020 |  | 1 | 0.75 | Gehad | Complete
| LH_CODE_LOGIN_021 |  | 1 | 0.75 | Ahmed | Complete
| LH_CODE_REGISTER_022 |  | 1 | 0.75 | Ahmed | Complete
| LH_CODE_REVIEW_REPORT |  | 3 | 4 | Gehad | Complete
WP_PO TASKS | LH_Release planing | Create | 2 | 2 | Eman | Complete
| LH_Creating backlog |  | 2 | 1.5 | Eman | Complete
| LH_Assigniing tasks |  | 3 | 2 | Eman | in progress | 65% | 2
| LH_testing strategy |  | 4 | 4 | Eman | Complete
WP_TC_Execution & BUG REPORT | LH_TC_LOGIN_001 | Create | 1.5 | 2 | Gehad | Complete
| LH_TC_REGISTER_002 |  | 1.5 | 2 | Hala | Complete
| LH_TC_USERHOME_003 |  | 1.5 | 2 | Omar | Complete
| LH_TC_CATEGORIES_004 |  | 1.5 | 2 | Gehad | Complete
| LH_TC_PUBLISHARTICLE_005 |  | 1.5 | 2 | Hala | Complete
| LH_TC_PUBLISHAUDIO_006 |  | 2 | 2.5 | Omar | Complete
| LH_TC_PUBLISHVIDEO_007 |  | 1.5 | 2.5 | Gehad | Complete
| LH_TC_ADMINHOME_008 |  | 1.5 | 2 | Hala | Complete
| LH_TC_DELETEPOST_009 |  | 1.5 | 2 | Omar | Complete
| LH_TC_DELETEUSER_010 |  | 1 | 1.25 | Ahmed | Complete
| LH_TC_NOTIFICATION_011 |  | 1 | 1.5 | Omar | Complete
WP_RTM | LH_UPDATE RTM | Create | 5 | 7 | Omar | in progress | 70% | 3
| LH_UPDATE RTM | Review | 1.5 |  | Ahmed | not Started
WP_ISSUES&LOGS | LH_ISSUESANDLOGS | Create | 1 | 1 | Mahmoud | Complete
WP_TEST SUMMARY REPORT | LH_TEST SUMMARY REPORT | Create | 1 | 1.5 | Ahmed | Complete

## ESTIMATED_TIME
Name | Available Time | Planed Time | Actual Time
Eman | 15 | 14.5 | 14
Omar | 30 | 18 | 24
Hala | 18 | 12 | 16.5
Gehad | 20 | 13 | 18.75
Mahmoud | 32 | 28.5 | 30
Ahmed | 30 | 23.5 | 26.5
Total | 145 | 109.5