## Version History
Version Number | Author | Updated Section | Date
v1.0 | Hala Eldaly | intial version | 2025-04-22
v1.1 | Gehad Ashry | Check reviews | 2025-04-22

## LH-TC-SYSTEMCONSTRAINS-REVIEWS
Date | Review ID | Reviewed Entity | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
2025-04-22 | LH_TC_SYSTEMCONSTRAINTS_REVIEW_001 | File Template | Hala Eldaly | v1.0 | Test case file is based on an outdated template. | Update the test case file to follow the latest template. | Gehad Ashry | Closed | Open
2025-04-22 | LH_TC_SYSTEMCONSTRAINTS_REVIEW_002 | Name of the Excel Sheet Tab for Test Cases | Hala Eldaly | v1.0 | The test case sheet tab is not named according to the standard naming convention. | Rename the sheet tab to "LH_TC_SYSTEMCONSTRAINTS" to match the correct format. | Gehad Ashry | Closed | Open
2025-04-22 | LH_TC_SYSTEMCONSTRAINTS_REVIEW_003 | LH-TC-SYSTEMCONSTRAINT-001 | Hala Eldaly | v1.0 | The test case specifies that the application should load within 3 seconds without any HTTP errors, which is a valid check. However, it lacks validation for potential runtime issues that may not be immediately visible through the application interface. Even though the application may load correctly, issues such as JavaScript errors or failed network requests (e.g., 4xx/5xx errors) might still occur in the background, which could impact the overall user experience. | Please add a step to check for any console errors or failed network requests in the browser's Developer Tools (DevTools). This can be done by inspecting the console and network tab to ensure there are no runtime errors or failed HTTP requests. | Gehad Ashry | Closed | Open
2025-04-22 | LH_TC_SYSTEMCONSTRAINTS_REVIEW_004 | LH-TC-SYSTEMCONSTRAINT-002 | Hala Eldaly | v1.0 | The test case confirms basic functionality across browsers, but to ensure full compatibility, it's recommended to also: 1) inspect DevTools for console/network errors and UI issues; 2) validate the app on different versions of each browser. | Add validation to test on different versions of each supported browser, and include checks for console/network errors in DevTools. | Gehad Ashry | Closed | Open
2025-04-22 | LH_TC_SYSTEMCONSTRAINTS_REVIEW_005 | LH-TC-SYSTEMCONSTRAINT-004 | Hala Eldaly | v1.0 | In the (Expected Results) column, there is extra spacing. | reduce the extra space by one to improve consistency | Gehad Ashry | NotApplicable | Open
2025-04-22 | LH_TC_SYSTEMCONSTRAINTS_REVIEW_006 | TC_ID Column (All TC IDs) | Hala Eldaly | v1.0 | All test case IDs contain a typo in the word "SYSTEMCONSTRAINT" — the trailing "S" is missing. | Update all test case IDs to use "SYSTEMCONSTRAINTS" instead of "SYSTEMCONSTRAINT". | Gehad Ashry | Closed | Open
2025-04-22 | LH_TC_SYSTEMCONSTRAINTS_REVIEW_007 | LH-TC-SYSTEMCONSTRAINT-002 | Hala Eldaly | v1.0 | The browser name "FireFox" is incorrectly capitalized. It should be written as "Firefox" with only the first "F" in uppercase. | Update the test step to reflect the correct spelling of the browser name: "Firefox". | Gehad Ashry | Closed | Open