## VERSION_HISTORY
version_number | Author | Updates | Date
V1.0 | Eman(PO) | planing for: 1:Test Cases (TC) 2:Wire Frame(WF) 3:Software Requirment Specifications 4:updating the pmp based on comments | 2025-04-14
v1.1 | Gehad Ashry | added the actual time for my tasks | 21/4/2025
v1.1 | Ahmed Abuzaid | added the actual time for already done tasks | 21/4/2025
v1.1 | Hala Eldaly | added the actual time for my tasks | 21/4/2025
v1.1 | Omar Sherif | added the actual time for my tasks | 21/4/2025
V1.1 | Eman(Po) | Adding the RTM tasks _Estimating the Rtm tasks _making tasks complete _Adding status column and filling it by data

## RELEASE_PLAN
WORK_PACKAGE _ID | Task_ID | type (Create/Review) | Estimated Hours | Actual Hours | Assigned Member | Status
WP_RP | LH_RP_SHEET_Create_1 | Create | 2hr | 4hr | Eman | Complete
| LH_RP_BACKLOG_Create_2 | Create | 2hr | 2hr | Eman | Complete
| LH_RP_TRACKING TASKS_3 | Create | 1:30hr | 5hr | Eman | Complete
WP_SRS | LH_SRS_REGISTERATION_1 | Create | 1:30hr | 2 hr | Ahmed | Complete
| LH_SRS_REGISTERATION_2 | Review | 45min | 45min | Mahmoud | Complete
| LH_SRS_LOGIN_3 | Create | 1hr | 1hr | Ahmed | Complete
| LH_SRS_LOGIN_4 | Review | 1hr | 1hr | Hala | Complete
| LH_SRS_NAVIGATION_5 | Create | 30min | 35 min | Ahmed | Complete
| LH_SRS_NAVIGATION_6 | Review | 45min | 30min | Omar | Complete
| LH_SRS_PUBLISH&UPLOAD_7 | Create | 1hr | 1:30hr | Ahmed | Complete
| LH_SRS_PUBLISH&UPLOAD_8 | Review | 30min | 45min | Gehad | Complete
| LH_SRS_NOTIFICATION_9 | Create | 20min | 15min | Ahmed | Complete
| LH_SRS_NOTIFICATION_10 | Review | 1hr | 45min | Eman | Complete
| LH_SRS_SYSTEM CONSTRAINS_11 | Create | 20min | 10min | Ahmed | Complete
| LH_SRS_SYSTEM CONSTRAINS_12 | Review | 45min | 30min | Mahmoud | Complete
| LH_SRS_ADMIN CONSTRAINS_13 | Create | 20min | 25min | Ahmed | Complete
| LH_SRS_ADMIN CONSTRAINS_14 | Review | 45min | 15min | Omar | Complete
| LH_SRS_ID CONSTRAINS_15 | Create | 20min | 30min | Omar | Complete
| LH_SRS_ID CONSTRAINS_16 | Review | 1hr | 10min | Hala | Complete
WP_TC | LH_TC_REGISTERATION_1 | Create | 2hr | 1:30hr | Omar | Complete
| LH_TC_REGISTERATION_2 | Review | 1hr | 45min | Eman | Complete
| LH_TC_LOGIN_3 | Create | 1:30 hr | 2hr | Hala | Complete
| LH_TC_LOGIN_4 | Review | 1hr | 1hr | Mahmoud | Complete
| LH_TC_NAVIGATION_5 | Create | 1hr | 1:30hr | Gehad | Complete
| LH_TC_NAVIGATION_6 | Review | 1hr | 1:15hr | Ahmed | Complete
| LH_TC_PUBLISH&UPLOAD_7 | Create | 1:30hr | 2:20hr | Ahmed | Complete
| LH_TC_PUBLISH&UPLOAD_8 | Review | 45min | 30min | omar | Complete
| LH_TC_NOTIFICATION_9 | Create | 1:30hr | 45min | Mahmoud | Complete
| LH_TC_NOTIFICATION_10 | Review | 30min | 45min | Gehad | Complete
| LH_TC_SYSTEMCONSTRAINS_11 | Create | 1hr | 1:30hr | Gehad | Complete
| LH_TC_SYSTEMCONSTRAINS_12 | Review | 1hr | 1:30hr | Hala | Complete
| LH_TC_ADMINCONSTRAINS_13 | Create | 1:30hr | 1hr | Eman | Complete
| LH_TC_ADMINCONSTRAINS_14 | Review | 45min | 15min | omar | Complete
| LH_TC_IDCONSTRAINS_15 | Create | 1:30hr | 45min | Mahmoud | Complete
| LH_TC_IDCONSTRAINS_16 | Review | 1:30hr | 1hr | Ahmed | Complete
WP_RTM | LH_RTM_REGISTER_1 | Create | 45min | 45min | Hala | in progress
| LH_RTM_LOGIN_2 | Create | 45min | 45min | Omar | Complete
| LH_RTM_PUBLISH&UPLOAD_3 | Create | 45min | 45min | Ahmed | Complete
| LH_RTM_NOTIFICATION_4 | Create | 45min |  | Mahmoud
| LH_RTM_IDCONSTRAINS_5 | Create | 45min |  | Mahmoud | not Started
| LH_RTM_ADMINCONSTRAINS_6 | Create | 45min | 45min | Eman | Complete
| LH_RTM_NAVIGATION | Create | 45min | 45min | Gehad | Complete
| LH_RTM_SYSTEMCONSTRAINS_7 | Create | 45min | 45min | Gehad | not Started
| LH_RTM_8 | Review | 2:30hr |  | Eman | not Started
WP_WF | LH_WF_REGISTERATION_1 | Create | 2hr | 1:15hr | Gehad | Complete
| LH_WF_REGISTERATION_2 | Review | 30min | 30 min | Ahmed | Complete
| LH_WF_LOGIN_3 | Create | 40min | 30min | Mahmoud | Complete
| LH_WF_LOGIN_4 | Review | 45min | 30min | Omar | Complete
| LH_WF_NAVIGATION_5 | Create | 3hr |  | Omar | in progress
| LH_WF_NAVIGATION_6 | Review | 1hr |  | Hala | not Started
| LH_WF_PUBLISH&UPLOAD_7 | Create | 2hr |  | Hala | not Started
| LH_WF_PUBLISH&UPLOAD_8 | Review | 1:30 |  | Gehad | not Started
| LH_WF_NOTIFICATION_9 | Create | 40 |  | Ahmed | not Started
| LH_WF_NOTIFICATION_10 | Review | 30min |  | Mahmoud | not Started
WP_PMP_UPDATE | LH_PMP_UPDATE_SEC1&2&3&4&5 | Create | 2hr |  | Hala | not Started | 1H
| LH_PMP_UPDATE_SEC_6&10 | Create | 3hr |  | Eman | not Started | 1H
| LH_PMP_UPDATE_SEC_7&8 | Create | 3hr |  | Hala | not Started | 1H
| LH_PMP_UPDATE_SEC_9&13 | Create | 2hr |  | Ahmed | not Started | 1H
| LH_PMP_UPDATE_SEC_11&12 | Create | 3hr |  | Mahmoud | not Started | 1H
| LH_PMP_UPDATE_SEC_14&15 | Create | 3hr |  | Omar | not Started | 2H
| LH_PMP_UPDATE_SEC1&2&3&4&5 | Review | 2hr |  | Gehad | not Started
| LH_PMP_UPDATE_SEC_6&10 | Review | 2hr |  | Ahmed | not Started
| LH_PMP_UPDATE_SEC_7&8 | Review | 2hr |  | omar | not Started
| LH_PMP_UPDATE_SEC_9&13 | Review | 2hr |  | Hala | not Started
| LH_PMP_UPDATE_SEC_11&12 | Review | 2hr |  | Mahmoud | not Started
| LH_PMP_UPDATE_SEC_14&15 | Review | 2hr |  | Eman | not Started

## ESTIMATED_TIME
Name | Available Time | Planed Time | Actual Time
Eman | 18 | 14 | 14:45
Omar | 14 | 13:45 | 6:45
Hala | 15:00 | 11:30 | 5:25
Gehad | 20 | 11:45 | 6:30
Mahmoud | 13 | 11:40 | 4:15
Ahmed | 17:00 | 14:30 | 10:15
Total | 97hr | 77hr | 47:55