## VERSION_HISTORY
version_number | Author | Updates | Date
V1.0 | Eman(PO) | planing for: | 14/04/2025
1:Test Cases (TC)
2:Wire Frame(WF)
3:Software Requirment Specifications
4:updating the pmp based on comments
v1.1 | Gehad Ashry | added the actual time for my tasks | 21/4/2025
v1.1 | Ahmed Abuzaid | added the actual time for already Done tasks | 21/4/2025
v1.1 | Hala Eldaly | added the actual time for my tasks | 21/4/2025
v1.1 | Omar Sherif | added the actual time for my tasks Estimating the Rtm tasks Adding the RTM tasks | 21/4/2025
V2.0 | Eman(PO) | Planning for 1:updating crs 2:updating Wire Frame(WF) 3:Designing architecture 4:Creating erd 5:Creating ui design | 28/4/2025
V2.1 | Eman(PO) | Updating time and status for tasks | 2025-03-05

## RELEASE_PLAN
WORK_PACKAGE _ID | Task_ID | type (Create/Review) | Estimated Hours | Actual Hours | Assigned Member | Status
WP_PO TASKS | LH_RELEASEPLAN_001 | Create | 3 | 5 | Eman | Complete
| LH_BACKLOG_002 |  | 2 | 2 | Eman | Complete
| LH_TRACKONG TASKS_003 |  | 3 | 4 | Eman | Complete
| LH_ISSUESANDLOGS_004 |  | 0.5 | 0.5 | Eman | Complete
WP_CRS | LH_CRS_LOGIN_001 | CREATE | 0.5 | 0.5 | Gehad | Complete
| LH_CRS_REGISTER_002 |  | 1 | 1 | Omar | Complete
| LH_CRS_USERHOME_003 |  | 1 | 1 | Hala | Complete
| LH_CRS_CATEGORIES_004 |  | 1 | 45min | omar | Complete
| LH_CRS_PUBLISHARTICLE_005 |  | 1 | 45 | Gehad | Complete
| LH_CRS_PUBLISHAUDIO_006 |  | 1 | 45 | Ahmed | Complete
| LH_CRS_PUBLISHVIDEO_007 |  | 1 | 45 | Hala | Complete
| LH_CRS_ADMINHOME_008 |  | 1 | 1 | Hala | Complete
| LH_CRS_DELETEPOST_009 |  | 1 | 50min | Ahmed | Complete
| LH_CRS_DELETEUSER_010 |  | 1 | 0.5 | Eman | Complete
| LH_CRS_NOTIFICATION_011 |  | 1 | 1 | Hala | Complete
| LH_CRS_SYSTEMCONSTRAINS_012 |  | 1 | 50min | Ahmed | Complete
| LH_CRS_LOGIN_013 | REVIEW | 0.5 | 0.5 | Hala | Complete
| LH_CRS_REGISTER_014 |  | 0.5 | 0.5 | Ahmed | Complete
| LH_CRS_USERHOME_015 |  | 0.5 | 0.5 | Ahmed | Complete
| LH_CRS_CATEGORIES_016 |  | 0.5 | 0.5 | Hala | Complete
| LH_CRS_PUBLISHARTICLE_017 |  | 0.5 | 0.5 | Mahmoud | Complete
| LH_CRS_PUBLISHAUDIO_018 |  | 0.5 | 25 | Gehad | Complete
| LH_CRS_PUBLISHVIDEO_019 |  | 0.5 | 25min | Omar | Complete
| LH_CRS_ADMINHOME_020 |  | 0.5 | 0.5 | Omar | Complete
| LH_CRS_DELETEPOST_021 |  | 0.5 | 45min | Gehad | Complete
| LH_CRS_DELETEUSER_022 |  | 0.5 | 0.5 | Hala | Complete
| LH_CRS_NOTIFICATION_023 |  | 0.5 | 0.5 | Mahmoud | Complete
| LH_CRS_SYSTEMCONSTRAINS_024 |  | 0.5 | 0.5 | Mahmoud | Complete
WP_WF | LH_WF_LOGIN_001 | CREATE | 0.5 | 0.5 | Eman | Complete
| LH_WF_REGISTER_002 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_USERHOME_003 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_CATEGORIES_004 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_PUBLISHARTICLE_005 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_PUBLISHAUDIO_006 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_PUBLISHVIDEO_007 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_ADMINHOME_008 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_DELETEPOST_009 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_DELETEUSER_010 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_NOTIFICATION_011 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_SYSTEMCONSTRAINS_012 |  | 0.5 | 0.5 | Eman | Complete
| LH_WF_LOGIN_013 | REVIEW | 0.5 | 0.5 | Hala | Complete
| LH_WF_REGISTER_014 |  | 0.5 | 0.5 | Ahmed | Complete
| LH_WF_USERHOME_015 |  | 0.5 | 0.5 | Ahmed | Complete
| LH_WF_CATEGORIES_016 |  | 0.5 | 0.5 | Hala | Complete
| LH_WF_PUBLISHARTICLE_017 |  | 0.5 | 0.5 | Mahmoud | Complete
| LH_WF_PUBLISHAUDIO_018 |  | 0.5 | 0.5 | Gehad | Complete
| LH_WF_PUBLISHVIDEO_019 |  | 0.5 | 0.5 | Omar | Complete
| LH_WF_ADMINHOME_020 |  | 0.5 | 0.5 | Omar | Complete
| LH_WF_DELETEPOST_021 |  | 0.5 | 0.5 | Gehad | Complete
| LH_WF_DELETEUSER_022 |  | 0.5 | 0.5 | Hala | Complete
| LH_WF_NOTIFICATION_023 |  | 0.5 | 0.5 | Mahmoud | Complete
| LH_WF_SYSTEMCONSTRAINS_024 |  | 0.5 | 0.5 | Mahmoud | Complete
WP_DESIGNARCHITECTURE | LH_ARCH_LOGIN_001 | CREATE | 3 | 1.5 | Mahmoud | Complete
| LH_ARCH_REGISTER_002 |  | 3.15 | 3 | Ahmed | Complete
| LH_ARCH_USERHOME_003 |  | 5.5 | 4 | Gehad | Complete
| LH_ARCH_CATEGORIES_004 |  | 6 | 4 | Hala | Complete
| LH_ARCH_PUBLISHARTICLE_005 |  | 3 | 3.5 | Eman | Complete
| LH_ARCH_PUBLISHAUDIO_006 |  | 4.5 | 3 | Omar | Complete
| LH_ARCH_PUBLISHVIDEO_007 |  | 4.5 | 2 | Omar | Complete
| LH_ARCH_ADMINHOME_008 |  | 6 | 4 | Hala | Complete
| LH_ARCH_DELETEPOST_009 |  | 3 | 2 | Mahmoud | Complete
| LH_ARCH_DELETEUSER_010 |  | 5.5 | 4 | Gehad | Complete
| LH_ARCH_SEQUANCEDIAGRAM_011 |  | 3 | 2 | Ahmed | Complete
| LH_ARCH_LOGIN_011 | Review | 1 | 1 | Eman | Complete
| LH_ARCH_REGISTER_012 |  | 2.25 | 1 | Omar | Complete
| LH_ARCH_USERHOME_013 |  | 2 | 1 | Mahmoud | Complete
| LH_ARCH_CATEGORIES_014 |  | 3 | 1 | Gehad | Complete
| LH_ARCH_PUBLISHARTICLE_015 |  | 2 | 1 | Mahmoud | Complete
| LH_ARCH_PUBLISHAUDIO_016 |  | 2.25 | 1 | Ahmed | Complete
| LH_ARCH_PUBLISHVIDEO_017 |  | 2.25 | 1 | Ahmed | Complete
| LH_ARCH_ADMINHOME_018 |  | 3 | 2 | Gehad | Complete
| LH_ARCH_DELETEPOST_019 |  | 3 | 1 | Hala | Complete
| LH_ARCH_DELETEUSER_020 |  | 2.25 | 1 | Omar | Complete
| LH_ARCH_SEQUANCEDIAGRAM_021 |  | 1 | 0.5 | Eman | Complete
WP_ERD | LH_ERD_001 | Create | 3 | 3 | Omar,AHMED | Complete
| LH_ERD_002 | Review | 3 | 2.5 | Gehad,Hala | Complete
WP_UI | LH_UI_001 | Create | 3 | 2 | Mahmoud | Complete
| LH_UI_002 | Review | 3 | 1.5 | Eman | Complete

## ESTIMATED_TIME
Name | Available Time | Estimated Time | Actual Time
Eman | 14 | 23.5 | 24.5
Omar | 8 | 18 | 11
Hala | 8 | 23 | 18
Gehad | 8 | 20.5 | 14.5
Mahmoud | 8 | 16 | 10.5
Ahmed | 8 | 19 | 14.5
Total | 54 | 120 | 93