## LH_WF_REGISTRATION_REVIEW
date | ID | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
22/4/2025 | LH-WF-REGISTRATION-REVIEW-001 | Ahmed Abuzaid | v1.0 | I see that the placeholder section didn't match our requirements | I prefer to make registration simple as possible, so we can only keep the logo section and the registration form ("email","user name","password") | Gehad | closed | closed
27/4/2025 | LH-WF-REGISTRATION-REVIEW-002 | Ahmed Abuzaid | v1.1 | back to SRS I found there are many error messages for many validations like existing user name or existing email or validations fro password | so I prefer to add some error messages "with red color" from the SRS to wireframe to make it more expressive, you can back to login wireframe to understand what I mean | Gehad | closed | closed

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Ahmed Abuzaid | Initial version of review on registration wireframe | 2025-04-22
v1.1 | Ahmed Abuzaid | close registration wireframe review and verify the updates | 2025-04-23
v1.2 | Ahmed Abuzaid | ask to add more details to registration form wireframe | 2025-04-27
v1.3 | Ahmed Abuzaid | close registration wireframe review, verify the updates and modify id naming convention | 2025-04-28