## REVIEW-SHEET
date | ID | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
17/4/2025 | LH_CRS_NOTIFICATION_Review_001 | Eman | V1.0 | At the notification feature the first crs need to be more atomic to contain only one action the user could do | make the CRS is as follow""Users can follow and unfollow specific categories." | Omar | not applicable
17/4/2025 | LH_CRS_NOTIFICATION_Review_002 | Eman | V1.1 | At notification feature the CRS is too vauge and does not explain what the customer want the system do | write the CRS as this"The system must notify users within the website interface when new content is added to a followed category." | Omar | closed
21/4/2025 | LH_CRS_SYSTEM_Review_003 | Omar Sherif | V1.8 | NO comments | N/A | Ahmed Abouzied | closed | closed
29/4/2025 | LH_CRS_LOGIN_Review_004 | Hala Eldaly | V1.9 | NO comments | N/A | Gehad Ashry | closed | closed

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Eman | review the notification feature and ask for some updates on it | 2025-04-17
v1.1 | Omar | review the system constraints and closed the reviewd notifications CRS | 2025-04-21
v1.2 | Hala Eldaly | review the login and No Comments | 2025-04-29