## VERSION_HISTORY
version_number | Author | Updates | Date
v3.0 | Eman(PO) | planing for: 1: update Software Requirment Specifications according to customer modification 2:test cases for the new srs 4:coding the featurs | 2025-05-02

## RELEASE_PLAN
WORK_PACKAGE _ID | Task_ID | type (Create/Review) | Estimated Hours | Actual Hours | Assigned Member | Status
WP_PO TASKS | LH_RELEASEPLAN_001 | Create | 3 |  | Eman
| LH_BACKLOG_002 |  | 2 |  | Eman
| LH_TRACKONG TASKS_003 |  | 3 |  | Eman
| LH_ISSUESANDLOGS_004 |  | 0.5 |  | Eman
WP_SRS | LH_SRS_LOGIN_001 | CREATE | 1 |  | Gehad
| LH_SRS_REGISTER_002 |  | 1 |  | Omar
| LH_SRS_USERHOME_003 |  | 1 |  | Hala
| LH_SRS_CATEGORIES_004 |  | 1 |  | omar
| LH_SRS_PUBLISHARTICLE_005 |  | 1 |  | Gehad
| LH_SRS_PUBLISHAUDIO_006 |  | 1 |  | Ahmed
| LH_SRS_PUBLISHVIDEO_007 |  | 1 |  | Hala
| LH_SRS_ADMINHOME_008 |  | 1 |  | Hala
| LH_SRS_DELETEPOST_009 |  | 1 |  | Ahmed
| LH_SRS_DELETEUSER_010 |  | 1 |  | Eman
| LH_SRS_NOTIFICATION_011 |  | 1 |  | Hala
| LH_SRS_SYSTEMCONSTRAINS_012 |  | 1 |  | Ahmed
| LH_SRS_LOGIN_013 | REVIEW | 0.5 |  | Hala
| LH_SRS_REGISTER_014 |  | 0.5 |  | Ahmed
| LH_SRS_USERHOME_015 |  | 0.5 |  | Ahmed
| LH_SRS_CATEGORIES_016 |  | 0.5 |  | Hala
| LH_SRS_PUBLISHARTICLE_017 |  | 0.5 |  | Mahmoud
| LH_SRS_PUBLISHAUDIO_018 |  | 0.5 |  | Gehad
| LH_SRS_PUBLISHVIDEO_019 |  | 0.5 |  | Omar
| LH_SRS_ADMINHOME_020 |  | 0.5 |  | Omar
| LH_SRS_DELETEPOST_021 |  | 0.5 |  | Gehad
| LH_SRS_DELETEUSER_022 |  | 0.5 |  | Hala
| LH_SRS_NOTIFICATION_023 |  | 0.5 |  | Mahmoud
| LH_SRS_SYSTEMCONSTRAINS_024 |  | 0.5 |  | Mahmoud
WP_TC | LH_TC_LOGIN_001 | CREATE | 1 |  | Gehad
| LH_TC_REGISTER_002 |  | 1 |  | Omar
| LH_TC_USERHOME_003 |  | 1 |  | Hala
| LH_TC_CATEGORIES_004 |  | 1 |  | omar
| LH_TC_PUBLISHARTICLE_005 |  | 1 |  | Gehad
| LH_TC_PUBLISHAUDIO_006 |  | 1 |  | Ahmed
| LH_TC_PUBLISHVIDEO_007 |  | 1 |  | Hala
| LH_TC_ADMINHOME_008 |  | 1 |  | Hala
| LH_TC_DELETEPOST_009 |  | 1 |  | Ahmed
| LH_TC_DELETEUSER_010 |  | 1 |  | Eman
| LH_TC_NOTIFICATION_011 |  | 1 |  | Hala
| LH_TC_SYSTEMCONSTRAINS_012 |  | 1 |  | Ahmed
| LH_TC_LOGIN_013 | REVIEW | 0.5 |  | Hala
| LH_TC_REGISTER_014 |  | 0.5 |  | Ahmed
| LH_TC_USERHOME_015 |  | 0.5 |  | Ahmed
| LH_TC_CATEGORIES_016 |  | 0.5 |  | Hala
| LH_TC_PUBLISHARTICLE_017 |  | 0.5 |  | Mahmoud
| LH_TC_PUBLISHAUDIO_018 |  | 0.5 |  | Gehad
| LH_TC_PUBLISHVIDEO_019 |  | 0.5 |  | Omar
| LH_TC_ADMINHOME_020 |  | 0.5 |  | Omar
| LH_TC_DELETEPOST_021 |  | 0.5 |  | Gehad
| LH_TC_DELETEUSER_022 |  | 0.5 |  | Hala
| LH_TC_NOTIFICATION_023 |  | 0.5 |  | Mahmoud
| LH_TC_SYSTEMCONSTRAINS_024 |  | 0.5 |  | Mahmoud
WP_WRITINGCODE | LH_CODE_LOGIN_001 | CREATE | 4 |  | Mahmoud
| LH_CODE_REGISTER_002 |  | 4 |  | Ahmed
| LH_CODE_USERHOME_003 |  | 4 |  | Gehad
| LH_CODE_CATEGORIES_004 |  | 4 |  | Hala
| LH_CODE_PUBLISHARTICLE_005 |  | 4 |  | Eman
| LH_CODE_PUBLISHAUDIO_006 |  | 4 |  | Omar
| LH_CODE_PUBLISHVIDEO_007 |  | 4 |  | Omar
| LH_CODE_ADMINHOME_008 |  | 4 |  | Hala
| LH_CODE_DELETEPOST_009 |  | 4 |  | Mahmoud
| LH_CODE_DELETEUSER_010 |  | 4 |  | Gehad
| LH_CODE_LOGIN_011 | Review | 3 |  | Mahmoud
| LH_CODE_REGISTER_012 |  | 3 |  | Ahmed
| LH_CODE_USERHOME_013 |  | 3 |  | Gehad
| LH_CODE_CATEGORIES_014 |  | 3 |  | Hala
| LH_CODE_PUBLISHARTICLE_015 |  | 3 |  | Eman
| LH_CODE_PUBLISHAUDIO_016 |  | 3 |  | Omar
| LH_CODE_PUBLISHVIDEO_017 |  | 3 |  | Omar
| LH_CODE_ADMINHOME_018 |  | 3 |  | Hala
| LH_CODE_DELETEPOST_019 |  | 3 |  | Mahmoud
| LH_CODE_DELETEUSER_020 |  | 3 |  | Gehad
WP_WRITINGCODE | LH_SRS_LOGIN_001 | CREATE | 4 |  | Mahmoud
| LH_CODE_REGISTER_002 |  | 4 |  | Ahmed
| LH_CODE_USERHOME_003 |  | 4 |  | Gehad
| LH_CODE_CATEGORIES_004 |  | 4 |  | Hala
| LH_CODE_PUBLISHARTICLE_005 |  | 4 |  | Eman
| LH_CODE_PUBLISHAUDIO_006 |  | 4 |  | Omar
| LH_CODE_PUBLISHVIDEO_007 |  | 4 |  | Omar
| LH_CODE_ADMINHOME_008 |  | 4 |  | Hala
| LH_CODE_DELETEPOST_009 |  | 4 |  | Mahmoud
| LH_CODE_DELETEUSER_010 |  | 4 |  | Gehad
| LH_CODE_LOGIN_011 | Review | 3 |  | Mahmoud
| LH_CODE_REGISTER_012 |  | 3 |  | Ahmed
| LH_CODE_USERHOME_013 |  | 3 |  | Gehad
| LH_CODE_CATEGORIES_014 |  | 3 |  | Hala
| LH_CODE_PUBLISHARTICLE_015 |  | 3 |  | Eman
| LH_CODE_PUBLISHAUDIO_016 |  | 3 |  | Omar
| LH_CODE_PUBLISHVIDEO_017 |  | 3 |  | Omar
| LH_CODE_ADMINHOME_018 |  | 3 |  | Hala
| LH_CODE_DELETEPOST_019 |  | 3 |  | Mahmoud
| LH_CODE_DELETEUSER_020 |  | 3 |  | Gehad

## ESTIMATED_TIME
Name | Available Time | Planed Time | Actual Time
Eman | 14 | 14
Omar | 11 | 10
Hala | 11 | 10
Gehad | 11 | 10
Mahmoud | 11 | 10
Ahmed | 11 | 10
Total | 69 | 64