## Sheet1
ID | Date | Title | Description | Cause | Impact | Action Taken | Status | Notes
1 | 2025-04-26 | RTM mismatch due to reordered test cases | Test cases were misaligned with unrelated SRS items due to manual reordering in the RTM. | Improper handling of test case order in the RTM. | RTM traceability became inaccurate; potential for incorrect validation. | Realigned test cases with correct SRS references and communicated the update to the team. | Closed | Training to be planned to avoid future reordering issues.
2 | 2025-04-28 | Team member sick - HLD, LLD, Class Diagrams delayed | A team member got sick and couldn’t deliver High Level Design, Low Level Flowcharts, and Class Diagrams for the Login and Delete Post features. | Unexpected health issue. | Delayed submission of design documents for key features. | Other team members covered partially; full update scheduled next sprint. | closed | Impact on current sprint timelines noted.
3 | 2025-05-02 | Design review delays due to misunderstanding | Team members delayed reviewing HLD, LLD, and Class Diagrams due to confusion on how to properly review the designs. | Lack of understanding of review expectations and design flow. | Slower feedback loop, risk of quality issues in implementation. | deciding that for the review :the design should cover at least the happy scenario | Open | Future reviews to be tracked with clearer checklist.
4 | 2025-04-26 | Wireframe changed completely due to requirement updates | Customer changed key requirements in a release planning meeting which led to a complete redesign of the previous wireframe. | Late-stage requirement changes from customer. | Significant time re-invested in redesign work. | Updated wireframes and informed all teams; resynced design schedule. | Closed | More frequent early feedback to be planned.
5 | 2025-04-29 | SRS update postponed after CRS changes | Following customer feedback, the CRS was updated, but the SRS update was postponed to the next release due to limited time. | Customer changes received late. | Current SRS version does not reflect updated requirements. | CRS updated immediately, SRS scheduled for next sprint update. | Open | Risk of inconsistency noted, needs validation.
6 | 2025-04-29 | Design based on Wireframe instead of updated SRS | Designs (HLD, LLD, Class Diagram) were developed based on the new customer-driven Wireframe instead of the outdated SRS due to time constraints. | Design had to start before updated SRS was available. | Design may drift from official documented requirements. | Used wireframe descriptions and a temporary document provided by lead; plan to align with updated SRS. | Open | Will cross-check with SRS once updated.