## Version History
Version Number | Author | Updated Section | Date
v 1.0 | Gehad Ashry | Creating Risk Register and added some potential risks that appeared during first week of work | 2025-04-13

## Risk Register
Risk ID | Description | Category | Probability | Impact | Severity | Response Strategy | Owner | Status | Date Identified | Comments
LH-Risk-001 | Missed milestones affecting project review and evaluation | Schedule | Medium | High | High | Set internal deadlines before actual milestone dates. | Team Lead | Open | 2025-04-12
LH-Risk-002 | Miscommunication between team and coach or among members | Communication | Medium | Medium | Medium | Follow communication plan, hold structured weekly meetings | Team Lead | Open | 2025-04-12
LH-Risk-003 | Team fails to apply naming conventions and config rules consistently | Configuration Mgmt | High | Medium | High | assign config review responsibility to a team member | Configuration Owner | Open | 2025-04-12
LH-Risk-004 | Late submission of progress reports impacting coach feedback | Reporting / Schedule | Medium | Medium | Medium | Set internal deadlines for report submission; use reminders and tracking sheets | Reporting Owner | Open | 2025-04-12
LH-Risk-005 | Inconsistent version control leading to overwritten or lost files | Technical / Process | Medium | High | High | Maintain a version control log with file summary on GitHub while keeping file name as it is. | Configuration Owner | Open | 2025-04-12
LH-Risk-006 | Overload of tasks on one or two team members (poor task distribution) | Team / Resource | High | Medium | High | Use RACI matrix to assign roles properly; review workload weekly | Team Lead | Open | 2025-04-12
LH-Risk-007 | Inadequate documentation of project artifacts and deliverables | Process / Quality | Medium | Medium | Medium | Assign a dedicated documentation lead; review docs weekly | Documentation Lead | Open | 2025-04-12
LH-Risk-008 | Team members may become unavailable due to exams, assignments, or personal matters | Resource / Schedule | High | Medium | High | Create a shared academic calendar; adjust task load in advance; ensure cross-training | Team Lead | Open | 2025-04-12
LH-Risk-009 | Project deadlines may overlap with academic submission weeks | Schedule | High | High | High | Plan critical tasks around known academic milestones; get early start on high-priority work | Team Lead | Open | 2025-04-12
LH-Risk-010 | Team may deprioritize project due to academic workload stress | Communication | Medium | Medium | Medium | Motivate through regular meetings, and visible progress tracking | Team Lead | Open | 2025-04-12
LH-Risk-011 | Lack of availability during weekends or holidays for team collaboration | Communication | High | Medium | High | Set default working hours early in the project; allow flexibility with notice | Team Lead | Open | 2025-04-12