## Version History
Version Number | Author | Updated Section | Date
v1.0 | Mahmoud abdelmageed | intial version | 2025-04-16

## Review sheet
date | Review ID | Reviewed Entity | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
2025-04-16 | LH_REVIEW_TC_LOGIN_001 | LH-TC-Login-001 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability 3- invalid test data, user can only login using email and password | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_002 | LH-TC-Login-002 | Mahmoud abdelmageed | 1.0 | 1-user is alread registered precondition is unnecessary 2- there is no space between the username and the password in the test data column 3-in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-remove the user is already registered precondition 2-change test data to the correct form 3-separate username(email) and password to different lines or add space between username and password 4-put each step in the steps column in a new line | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_003 | LH-TC-Login-003 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_004 | LH-TC-Login-004 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_005 | LH-TC-Login-005 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_006 | LH-TC-Login-006 | Mahmoud abdelmageed | 1.0 | 1-there is no space between the username and the password in the test data column 2- in the steps column steps index number is mixed with the steps data because there are no spaces, bad redability | 1-change test data to the correct form 2-separate username(email) and password to different lines or add space between username and password 3-put each step in the steps column in a new line | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_007 | LH-TC-Login-007 | Mahmoud abdelmageed | 1.0 | this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_008 | LH-TC-Login-008 | Mahmoud abdelmageed | 1.0 | this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_009 | LH-TC-Login-009 | Mahmoud abdelmageed | 1.0 | this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_010 | LH-TC-Login-010 | Mahmoud abdelmageed | 1.0 | this feature is out of scope | 1-delete testcase because its out of scope | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_011 | File name | Mahmoud abdelmageed | 1.0 | File name is using - for spacing instead of _ | 1-Change filename to follow the naming convention | Hala Eldaly | Open | Open
2025-04-16 | LH_REVIEW_TC_LOGIN_012 | Sign up button | Mahmoud abdelmageed | 1.0 | the feature (new user? Sign up) button was not tested | 1-include testcases to test this feature | Hala Eldaly | Open | Open