## LH_WF_DELUSER_REVIEW
date | ID | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
29/4/2025 | LH-WF-DELUSER-REVIEW-001 | Omar Sherif | v1.0 | The wireframe shows "Search by Username" but lacks a User ID search option, as required by the SRS. | Add a second input field labeled "Search by User ID" or include a toggle button (e.g., "Search by: Username / ID") to switch modes. | Eman | not applicable | open
29/4/2025 | LH-WF-DELUSER-REVIEW-002 | Omar Sherif | v1.0 | No visual indication of how search results are displayed (e.g., user details after a search). | Add a placeholder section below the search bar to dynamically show user details (e.g., User ID, Username) only after a search is executed. | Eman | closed | open
29/4/2025 | LH-WF-DELUSER-REVIEW-003 | Omar Sherif | v1.0 | Missing confirmation step to prevent accidental deletions. | Add a modal/popup in the wireframe after clicking "Delete" with the message: "Delete User123 and all their content? This action cannot be undone." Buttons: "Cancel" (primary) / "Delete" (secondary). | Eman | not applicable | open
29/4/2026 | LH-WF-DELUSER-REVIEW-004 | Omar Sherif | v1.0 | The "Delete" button’s prominence may lead to accidental clicks. | Reposition the "Delete" button away from the search bar (e.g., below user details) and style it as a secondary button (e.g., red outline). | Eman | closed | open

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Omar Sherif | Initial version of review on Delete user wireframe | 2025-04-29
v1.2 | eman | update owner status