## REVIEW-SHEET
date | ID | Reviewer | Version | Review Comments | Actions | Owner | Owner Status | Reviewer verification
2025-04-04 | LH_REVIEW_SIQ_001 | Hala Eldaly | v1.3 | IDs naming convention doesn't follow the rules. | Review and update all ID naming conventions to align with the defined project standards | Mahmoud Radi | closed | closed
2025-04-04 | LH_REVIEW_SIQ_002 | Hala Eldaly | v1.3 | Registration feature is written incorrectly. | Please review spelling |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_003 | Hala Eldaly | v1.3 | SIQ_02 – This question should be: (Should the password contain a combination of letters, numbers, and special characters?) NOT: (Should the password be a combination between numbers, chars and special chars?) | Be clear about the difference between chars (characters) and words. |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_004 | Hala Eldaly | v1.3 | SIQ_06 – It's not related to the registration feature, but to performance. | Reclassify SIQ_06 under performance category instead of registration. |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_005 | Hala Eldaly | v1.3 | SIQ_08 – This question should be: (Should the website include exactly 5 content categories?) NOT: (Should there be 5 categories?) | Update SIQ_08 wording to: "Should the website include exactly 5 content categories?" for clarity. Update SIQ_08 wording to: "Should the website include exactly 5 content categories?" for clarity. |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_006 | Hala Eldaly | v1.3 | SIQ_10 – This question should be: (Should the maximum allowed audio recording size be 20 MB?) NOT: (Should the maximum size for recordings not exceed 20mb?) | Aim for clear and formal phrasing in question wording to avoid ambiguity. |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_007 | Hala Eldaly | v1.3 | SIQ_11 – Confusing: chars vs. words >> Should the maximum length of an article be limited to 1000 words? | Clarify SIQ_11 by specifying "1000 words" instead of using ambiguous terms like "chars" |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_008 | Hala Eldaly | v1.3 | SIQ_13 – "Mp3" → Should the audio format be MP3 only? | Focus on consistent capitalization ( use MP3 instead of Mp3) |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_009 | Hala Eldaly | v1.3 | SIQ_14 – This question should be: (Should a notification system be available through the website?) NOT: (A notification system should be available via website?) | Rephrase SIQ_14 to: "Should a notification system be available through the website?" to maintain consistency and proper question format. |  | closed | closed
2025-04-04 | LH_REVIEW_SIQ_010 | Hala Eldaly | v1.3 | SIQ_16 – Incorrect structure >> Should the admin features include removing articles, videos, and audio files? | Revise SIQ_16 to: "Should the admin features include removing articles, videos, and audio files?" to correct the sentence structure. |  | closed | closed
14/4/2025 | LH_REVIEW_SIQ_011 | Gehad Ashry | v1.4 | SIQ_17: Does this feature mean to permanently delete a user or just suspend his account? | Clarify SIQ_17 >> Recommendation: Should the admin be able to deactivate or remove a user from the system? |  | open
14/4/2025 | LH_REVIEW_SIQ_012 | Gehad Ashry | v1.4 | SIQ_19: Could be merged with the login question (SIQ_18) or clarified to avoid redundancy | Clarify SIQ_19 >> Recommendation: Should access to the system be restricted to users who have registered? |  | open
14/4/2025 | LH_REVIEW_SIQ_013 | Gehad Ashry | v1.4 | SIQ_20: not well structured | Rephrase SIQ_20 >> Recommendation: Should the system display a simple error message if login information is incorrect or incomplete? |  | open
14/4/2025 | LH_REVIEW_SIQ_014 | Gehad Ashry | v1.4 | SIQ_21: not well structured | Rephrase SIQ_21 >> Recommendation: Should user passwords be stored securely using basic hashing methods? |  | open
14/4/2025 | LH_REVIEW_SIQ_015 | Gehad Ashry | v1.4 | SIQ_22: not well structured | Rephrase SIQ_22 >> Recommendation: Should the registration form require all fields (email, username, and password) to be filled out? |  | open
14/4/2025 | LH_REVIEW_SIQ_016 | Gehad Ashry | v1.4 | SIQ_23: What exactly is meant by 'Special Characters' ? | Clarify and Rephrase SIQ_23 >> Recommendation: Should usernames follow specific rules such as 4–20 characters and only contain letters and numbers? |  | open
14/4/2025 | LH_REVIEW_SIQ_017 | Gehad Ashry | v1.4 | SIQ_24:Doesn’t define what counts as a duplicate—email? username? | Clarify and Rephrase SIQ_24 >> Recommendation: Should the system prevent multiple registrations using the same email or username? |  | open
14/4/2025 | LH_REVIEW_SIQ_018 | Gehad Ashry | v1.4 | SIQ_25: Does not define what 'specific format' | Clarify and Rephrase SIQ_25 >> Recommendation: Should the system automatically assign user IDs in a simple, consistent format (e.g., U001, U002)? |  | open

## VERSION-HISTORY
Version number | Author | Updated section | Date
v1.0 | Hala Eldaly | intial version | 2025-04-07
v1.1 | Hala Eldaly | I separated the Review Comments into individual rows for better control and organization. | 2025-04-12
v1.2 | Gehad Ashry | Reviewed SIQ v1.4 | 2025-04-14